## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate (hours) | Sprint Review
Database RDS linked to SQL Workbench | 4
Set up the RDS in Amazon and ensure settings are right |  | Kate | Done | 1 | 3
Link the AWS with workbench |  | Kate | Done | 1 | 5
Separate out the design of the tables. Ensure that static data is captured apart from the webcrawler data. |  | Kate | Done | 1 | 1
Validate that the database is returning and showing consistant and logical data, update the python code if not. |  | Kate | Done | 1 | 4
Python web crawler code | 4
Ensure the code runs continuously on EC2 via terminal argparse command |  | Kate | Done | 1 | 2
Ensure the code has a flat file capture default |  | Kate | Done - but cannot find the file on EC2 so not working | 1 | 2
Ensure the code sleeps every 5 mins |  | Kate | Done | 0.5 | 0.05
Ensure the connection close function is working |  | Kate | Error - do not have proper error validation in the simple code without this | 1 | 2
Flask set up and validation to EC2 localhost on browser | 4
Download flask and associated apache etc to EC2 instance |  | Kate | Done | 1 | 3
Ensure security settings are updated in EC2 |  | Kate | Done | 0.2 | 0.5
Validate the Flask app with hello world appearing 200 success message on terminal |  | Kate | Done | 0.2 | 0.5
Validate the Flask app with hellow world appearing on browser |  | Kate | Done | 0.2 | 1.5
Googlemap and map pointers | 8
Create basic webpage with google maps and pointers offline |  | Kate | Done | 2 | 3
Ensure correct weather info is captured using javascript |  | Kate | Done | 6 | 2
Ensure data requested from users is tying to the weather displayed and specific to the pointer selected using javascript |  | Kate | Done for weather | 1 | 0
Link colour of pointers via OL in hml to db search (SQL or python) |  | Pan | Not started | 1 | 0
For graphs, ensure that mathplotlib or similar is installed and that graphs will display correctly via html |  | Kate | Not started | 1 | 0
Python/SQL query code via Flask to DB | 8
Write sample queries to the flask application linked to the html buttons |  | Kate | Done | 1 | 0
Using python pandas so ensure that we can see the database on the terminal |  | Kate | Done | 0.2 | 0.3
Replace the hello world py file with a proper Dublin bikes python template for flask - containing the html site created offline and the queries above |  | Kate | Done | 1 | 0
Ensure the flask file has simple queries from the database using OL dropdown buttons in html for user |  | Kate | Done | 1 | 0
Ensure graphs queries have links with user request above. |  | Kate | Not started | 1
Total |  | Kate |  | 19.1 | 29.55
Create a Sprint Backlog in Smartsheet